# Date: 27th November, 2025

# DES–myelin Joint Project Plan

### NEP-2020 Readiness Index & Implementation Study

A 12-week collaborative academic and research initiative
(Aligned to MoU: 17 Nov 2025)

# 1. Project Purpose

This study aims to:

- Assess NEP-2020 readiness across 50+ DES schools.

- Develop school-level and cluster-level NEP Readiness Index.

- Evaluate teacher cognitive & computational capability using myelin’s Teacher Diagnostic.

- Identify gaps in:

  - Learning diagnostics

  - Teacher maturity

  - HPC readiness

  - Leadership & implementation culture

  - Parent–community involvement

- Deploy low-cost, low-effort interventions aligned to NEP-2020.

- Produce a joint research report with actionable NEP-2020 implementation playbook for other schools to refer.

# 2. Project Outcomes (for DES & myelin)

### DES Will Receive:

- School-wise 100-point NEP Readiness Index

- Teacher maturity insights (via Teacher Diagnostic)

- Category-wise gaps & action priorities

- Evidence from real classroom interventions

- A research-backed NEP model for state-scale replication

- Strengthened parent & community engagement signals

- Preliminary HPC (PARAKH-aligned) practices

### myelin Will Achieve:

- Validation of teacher maturity (TEMM) & readiness framework

- Cluster-level data on teacher cognitive & computational capabilities

- Intervention effectiveness insights

- Strengthening NEP-aligned diagnostic & intervention ecosystem

- A replicable model for larger networks

This project lays the foundation for a multi-year NEP implementation roadmap.

# 3. 12-Week Implementation Timeline

## Phase 1 — Mobilisation & Orientation (Weeks 1-2)

### Key Activities

- MoU Signing & Kick-off Meeting

- DES nominating participating schools

- Appoint 1 coordinator per school/cluster

- Orientation by myelin on:

  - NEP-2020 Readiness Framework

  - Data collection formats

  - Diagnostic tools (student + teacher)

  - PLC protocols

  - Low-cost intervention philosophy

- Teacher Communication Rollout (Critical New Step)
A formal message to teachers explaining:

  - Why diagnostics matter

  - NEP-2020’s 5 principles & 5Cs

  - Purpose of their Teacher Cognitive Diagnostic

  - Assurance of anonymity & non-punitive usage

- Technical & Admin Setup

- Collaborative communication

- Report templates

### Deliverables

- Orientation decks

- Teacher communication letter

- Coordinator handbook

- Data collection templates

## Phase 2 — Baseline Readiness & Teacher Diagnostics (Weeks 2–4)

### A. Teacher Cognitive & Computational Diagnostic

Purpose: Understand how teachers think, not what they know.
Assesses:

- Bloom’s levels (apply–analyse–evaluate–create)

- Computational thinking (decomposition, abstraction, pattern recognition)

- Reasoning, inference, logical structuring

Output:

- Teacher maturity indicators (feeding into TEMM)

- Cluster-level cognitive capability baseline

- Insights for differentiated professional development

### B. School Readiness Assessment

- Teacher self-assessment

- PLC culture check

- Leadership interviews

- Review of lesson plans & prior assessments

### C. Baseline Classroom Observations

Sampling-based (resource-light) review of:

- Questioning patterns

- Use of LO codes

- Engagement & differentiation

### D. Champion teachers and capacity building workshop

DES will nominate 2–3 teachers per school based on interest, diagnostic scores, prior NEP exposure, and principal recommendation. Conduct workshop for maximum 60 champion teachers on NEP foundational principles:

- Each child is unique

- Diagnosing learning levels

- Competency-based learning

- Teacher upskilling

### Deliverables

- Teacher Diagnostic Score Report (individual + anonymous institutional view)

- School Baseline Readiness Data Pack

(Minimal myelin travel — 1–2 visits max

Note: Baseline observations may be sampling-based across clusters to reduce load.

## Phase 3 — Interventions & Midline Review (Weeks 5–8)

### Low-Cost / Low-Effort Interventions

Aligned with DES feasibility and NEP-2020:

- Daily 5-minute teacher reflection loop

- LO-linked questioning patterns

- PLC meeting redesign

- Simple 4C tracking (HPC precursor)

- Parent home-learning nudges

- Mini-diagnostics (student-level)

### Champion cohort group review (virtual) to share evidence, challenges, and initial insights.

### myelin Role

- Provide templates

- Limited remote guidance

- Observe only representative PLCs & classes

### Midline Reflection

- Report early trends

- Leadership review

- Identify quick wins vs systemic blockers

### Deliverables

- Midline analysis & discussion deck

- Adjusted intervention plans

## Phase 4 — Index Creation & Final Research Report (Weeks 9–12)

### Activities

- Scoring of NEP Readiness Index across 5 categories:

  - Diagnostic readiness

  - Teacher maturity

  - HPC readiness

  - Leadership culture

  - Parent–community involvement

- Consolidating teacher maturity findings

- Building DES-wide benchmarking

- Drafting Joint Research Report

- Joint review & final editing

- Presentation to DES Governing Body

### Deliverables

- NEP Readiness Index (school, cluster, DES-wide)

- Teacher Diagnostic Insights Summary

- Joint Research Report

- 3-Month “NEP Action Roadmap”

- Closing presentation

# 4. Governance & Roles

### Steering Committee (Monthly)

- DES Academic Leadership

- myelin Leadership

### Working Group (Weekly)

- Coordinators

- myelin academic team

### Operational Group (Daily)

- Teachers

- Cluster coordinators

- myelin remote support team

Cluster coordinators will be responsible for ensuring school-level compliance

# 5. DES Responsibilities

- School nomination (30+)

- Teacher participation enforcement

- Facilitating teacher diagnostics & interviews

- Ensuring PLC & classroom access

- Supporting data collection

- Reviewing interim & final outputs

DES will arrange a principal orientation to ensure school-level buy-in and smooth execution.

# 6. myelin Responsibilities

- Provide NEP Readiness Toolkit

- Provide Teacher Diagnostic materials

- Facilitate baseline + midline + final analysis

- Develop Readiness Index & reports

- Recommend practical interventions

- Limit travel & cost (non-commercial clause)

- Build teacher maturity profiles (using TEMM mapping)

myelin will share periodic status updates (brief format) every fortnight.

# 7. Success Metrics

### For DES

- Readiness Index clarity

- Improved teacher practices (4Cs, questioning, reflection)

- Early HPC culture

- Leadership data-driven decision-making

- Better parent communication on competencies

### For myelin

- High-quality baseline data

- Validated diagnostic & maturity models

- Proven intervention effectiveness

- Scalable cluster execution model

Quality of teacher diagnostic participation (minimum 80%)

# 8. Risk & Mitigation

| Risk | Mitigation |
| --- | --- |
| Low teacher participation | Principal + coordinator alignment + clear communication |
| Data inconsistency | Templates + coordinated weekly checks |
| Teacher anxiety about diagnostics | Communication package + anonymity assurance |
| Limited field access | Prior scheduling; sampling; remote support |
| myelin bandwidth limits | Sampling-based observations; planned analytics load |

Teacher diagnostic quality might reduce if teachers “just attempt it to get done.

Mitigation to prevents superficial participation:

- Pre-communication + reassurance

- 1 short demo question during orientation

- Anonymous reporting reinforcement

- Principal verbal endorsement

# 9. Next Steps (Immediate)

- Finalize this Project Plan with DES

- myelin prepares:

  - Teacher Diagnostic tools

  - Coordinator orientation deck

  - Teacher communication package

  - Intervention templates

- DES prepares:

  - School list

  - Coordinator list

  - Teacher communication rollout

- Kick-off meeting (Week 1)

- Teacher Diagnostic Implementation (Week 2–3)

Schedule first Steering Committee sync before Week 1 begins.

CONFIDENTIALITY OF PROPOSALS: This proposal is strictly for the consumption of the parties to whom it is submitted. Prices and features quoted are confidential. No prices - accepted or rejected - will be shared with other prospective bidders, before, during, or after the process. Information acquired by the bidder, and upon award of the bid if applicable, Participant contact information, must remain confidential and in no way shared with competitors or counterparts of Zenworks and/or bidder before, during, or after the process. This request for proposal is not an offer to do business but simply a request for information.